## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Reshma | 2026-07-12 | Groq API key error crashes orchestrator instead of failing back gracefully | Sprint 1 | Reshma | Logical | Wrapped agent instantiation and API checks with fallback handling | 2026-07-12 | Closed | Verified in test_orchestrator.py
2 | Reshma | 2026-07-22 | PandasAuditTool throws FileNotFoundError if contract CSV path is invalid | Sprint 2 | Reshma | Logical | Added pre-checks for csv file path and returned structured error status | 2026-07-23 | Closed | Tested with valid/invalid paths
3 | Reshma | 2026-07-28 | ReviewAgent not triggered for liability-related high-risk clauses | Sprint 2 | Reshma | Logical | Extended risk check function to cover liability and breach key phrases | 2026-07-29 | Closed | Verified high_risk_review path routing
4 | Reshma | 2026-08-02 | ShortTermMemory window overflowed max limit when appending multiple steps | Sprint 3 | Reshma | Logical | Implemented max_window slicing logic in add_to_short_term | 2026-08-02 | Closed | Verified in test_memory.py
5 | Reshma | 2026-08-04 | VendorRiskApiTool raised UnboundLocalError on unregistered vendor name | Sprint 3 | Reshma | Data / Logical | Added default unknown vendor profile fallback dictionary in vendor_api.py | 2026-08-04 | Closed | Verified in test_tools.py
6 | Reshma | 2026-08-05 | Dashboard report download endpoint failed when report file did not exist | Sprint 3 | Reshma | User Interface / API | Added FileResponse check and standard 404 JSON response in api/app.py | 2026-08-06 | Closed | Tested via FastAPI endpoint
7 | Reshma | 2026-08-06 | Evaluator node threw ZeroDivisionError on empty quality dimensions input | Sprint 3 | Reshma | Logical | Added safeguard check returning default score 0.0 on empty inputs | 2026-08-06 | Closed | Verified pipeline safety

## Sheet2
Logical
User Interface
Maintainability
Standards
Others